## Simple Gantt Chart - EX
RescueRoute Gantt Chart
PROJECT TITLE | Rescue Route
PROJECT MANAGER | Bilal moutassim
COMPANY NAME | EMSI
DATE | 20/11/2024
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | QAP | Abdelhamid | 2024-10-11 | 13/11/24 |  | 100%
1.1.1 | Project intiation and task distribution | Bilal | 2024-11-11 | 14/11/24 |  | 100%
1.2 | Dockerize project | Amine | 13/11/24 | 14/11/24 |  | 90%
1.3 | Draw the UI in figma | Hamza | 14/11/24 | 15/11/24 |  | 100%
2 | Project Launch and Execution
2.1 | Test the free map api's services | Hamza | 14/11/24 | 20/11/24 |  | 100%
2.2 | Login backend function | Bilal | 18/11/24 | 20/11/24 |  | 100%
2.3 | Initialize sonarqube services | Amine | 19/11/24 | 20/11/24 |  | 100%
2.4 | Login UI | Nizar | 21/11/24 | 25/11/24 |  | 100%
3 | Project Development / Monitoring
3.1 | Selenium tests | Hamza | 25/11/24 | 28/11/24 |  | 90%
3.2 | Junit tests | Bilal | 25/11/24 | 28/11/24 |  | 90%
3.3 | SonarQube Repport | Amine | 25/11/24 | 28/11/24 |  | 90%
3.4 | Crud User | Nizar | 25/11/24 | 27/11/24 |  | 100%
3.5 | Crud Hospital | Abdelhamid | 25/11/24 | 27/11/24 |  | 100%
4 | Project Development / Monitoring
4.1 | Mobile Start + login page | Hamza | 27/11/24 | 29/11/24 |  | 100%
4.2 | Mobile map page implementation | Bilal | 27/11/24 | 29/11/24 |  | 100%
4.3 | CI / CD implemenetation | Amine | 26/11/24 | 2024-02-12 |  | 100%
4.4 | UI Crud user | Nizar | 26/11/24 | 28/11/24 |  | 100%
4.5 | UI Crud Hospital | Abdelhamid | 26/11/24 | 28/11/24 |  | 100%
5 | Project Development / Monitoring
5.1 | Appium implementation | Hamza |  |  |  | 50%
5.2 | Cloud implementation | Bilal |  |  |  | 50%
5.3 | Jenkins implementation | Amine |  |  |  | 50%
5.4 |  | Nizar |  |  |  | 0%
5.5 |  | Abdelhamid |  |  |  | 0%